## Projektoversigt
From Works Architects
Projekt |  | Status | Start | Slut | Bemærkninger
Inspirations Søgning | 100% | ¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦ | 2013-11-18 | 2013-11-18 | Graphicriver, rundt på nettet.
Business Card / Paper Mockups | 100% | ¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦ | 2013-11-18 | 2013-11-22 | Preview af Logo på brevpapir, visitkort, mm.
Design Photoshop | 100% | ¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦ | 2013-11-18 | 2013-11-20
Foundation Markup | 100% | ¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦ | 2013-11-20 | 2013-11-20 | Foundation Framework
HTML5 / CSS3 Markup | 37.51% | ¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦ | 2013-11-20 | 2013-11-21 | HTML5 / SASS = CSS3
| 0.01% |  | 0 | 0
CMS System | 68.19% | ¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦ | 2013-11-25 | 2013-11-29 | Sæt Basic CMS op!
| 0.01% |  | 0 | 0
Deadline | 0.01% |  | 2013-11-18 | 2013-11-23
Formulas:
Start = MIN(IF((Opgaver[Projekt]=Projekter[[#This Row],[Projekt]])*(Opgaver[Start]>0),Opgaver[Start]))
Slut = MAX(IF((Opgaver[Projekt]=Projekter[[#This Row],[Projekt]])*(Opgaver[Start]>0),Opgaver[[Start]:[Slut]]))
Opgaveoplysninger

## Opgaveoplysninger
Opgaveoplysninger
Start | Slut | Projekt | Opgave | Udført | Time Estimering | Bemærkninger
2013-11-18 | 2013-11-18 | Inspirations Søgning | Find inspiration på themeforrest.net | 1 | 50:00 | sd
2013-11-18 | 2013-11-18 | Inspirations Søgning | Find inspiration på uden for Pinterest | 1 | 50:00
2013-11-18 | 2013-11-19 | Design Photoshop | Mock up af Mobile Layout Forside | 1 | 100:00 | Forside Layout
2013-11-18 | 2013-11-20 | Design Photoshop | Mock up af Desktop layout Forside | 1 | 77:00 | 1280 Px Wide Grid
2013-11-18 | 2013-11-20 | Foundation Markup | Install Ruby | 1 | 0:05
2013-11-18 | 2013-11-20 | Foundation Markup | Install SASS, Foundation | 1 | 0:05
2013-11-20 | 2013-11-21 | HTML5 / CSS3 Markup | Install Brackets Mark 34 | 1 | 0:05
2013-11-20 | 2013-11-21 | HTML5 / CSS3 Markup | Sæt op boilerplate til Foundation | 1 | 0:05
2013-11-20 | 2013-11-21 | HTML5 / CSS3 Markup | Sæt op HTML/SASS/CSS for basic |  | 4:00
2013-11-20 | 2013-11-22 | HTML5 / CSS3 Markup | Forside Layout |  | 1:30
2013-11-20 | 2013-11-22 | HTML5 / CSS3 Markup | 2 Collum Layout |  | 2:00 | Nyheds side, Projekt
2013-11-20 | 2013-11-22 | HTML5 / CSS3 Markup | Grid Galleri Layout |  | 4:00 | Galleri
2013-11-20 | 2013-11-22 | HTML5 / CSS3 Markup | Kontakt Layout |  | 1:30
2013-11-19 | 2013-11-20 | Business Card / Paper Mockups | Brevpapir, logo, visitkort, preview | 1 | 2:00
2013-11-20 | 2013-11-20 | HTML5 / CSS3 Markup | Font awesome.sass install | 1 | 0:10
2013-11-25 | 2013-11-29 | CMS System | Design | 1 | 5:00
2013-11-25 | 2013-11-29 | CMS System | Basic HTML/CSS/SASS | 1 | 7:00
2013-11-25 | 2013-11-29 | CMS System | Code Pages | 1 | 3:00 | Mangler Template, Media Picker, Tags,
2013-11-25 | 2013-11-29 | CMS System | Code Projects | 1 | 5:00 | Mangler Media Picker, Tags, Categori
2013-11-25 | 2013-11-29 | CMS System | Code News | 1 | 3:00 | Mangler Media Picker, Tags, Categori
2013-11-25 | 2013-11-29 | CMS System | Code Users | 1 | 3:00 | Mangler Pass words og Image
2013-11-25 | 2013-11-29 | CMS System | My Profile (Go to Edit This userID) | 1 | 1:00
2013-11-25 | 2013-11-29 | CMS System | DashBoard Quick News | 1 | 2:00
2013-11-25 | 2013-11-29 | CMS System | Dashboard Right now | 1 | 2:00
2013-11-25 | 2013-11-29 | CMS System | Pages Sort Ajax |  |  | Later
2013-11-25 | 2013-11-29 | CMS System | Pages Media Picker
2013-11-25 | 2013-11-29 | CMS System | Pages Template |  |  | Feature Building
2013-11-25 | 2013-11-29 | CMS System | Media Everything
2013-11-25 | 2013-11-29 | CMS System | Projects Tags | 1 | 1:30
2013-11-25 | 2013-11-29 | CMS System | Projects MediaPicker
2013-11-25 | 2013-11-29 | CMS System | News Tags | 1 | 1:30
2013-11-25 | 2013-11-29 | CMS System | News Media Picker
2013-11-25 | 2013-11-29 | CMS System | Users Create, Functional | 1 | 2:00
2013-11-25 | 2013-11-29 | CMS System | Users Edit, Functional | 1 | 1:00 | Password Mangler
2013-11-25 | 2013-11-29 | CMS System | Users Profile Image |  |  | Not Yet
2013-11-25 | 2013-11-29 | CMS System | Users Role Aggisnment | 1 |  | Default admin
2013-11-25 | 2013-11-29 | CMS System | Settings Everything | 1 |  | Ajax get Zipcodes
Projektoversigt